## Hoja1
ID | Task Name | Execution Time (days) | Designated Member | Completed By | Start date | End Date | 10/31/23 | 2023-01-11 | 2023-02-11 | 2023-03-11 | 2023-04-11 | 2023-05-11 | 2023-06-11 | 2023-07-11 | 2023-08-11 | 2023-09-11 | 2023-10-11 | 2023-11-11 | 2023-12-11 | 11/13/23
B01 | Database Creation |  | Zack | Zack | 10/31/23 | 10/31/23
B02 | API REST Development | 4 |  | Zack | 10/31/23 | 2023-06-11
B02.1 | Server Setup | 1 | Mauro | Zack | 10/31/23 | 2023-02-11
B02.1.1 | General Middleware Setup |  | Mauro | Zack | 10/31/23 | 2023-02-11
B02.1.2 | Routes Definition |  | Mauro | Zack | 10/31/23 | 2023-02-11
B02.1.3 | Database Connection |  | Mauro | Zack | 10/31/23 | 2023-02-11
B02.2 | Routers Development | 3 | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.1 | Age Ratings Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.2 | Countries Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.3 | Categories Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.4 | Ratings Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.5 | Series Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.6 | Authors Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.7 | Genres Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.8 | Languages Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.9 | Covers Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.10 | Companies Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.11 | Colors Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.12 | Materials Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.13 | Sizes Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.14 | Subcategories Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.15 | Comics Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.16 | Collectibles Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.17 | Clothes Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.18 | Products Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.19 | Users Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.20 | Auth Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.21 | Orders Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.22 | Anouncements Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.2.23 | Comments Router |  | Zack | Zack | 2023-03-11 | 2023-05-11
B02.3 | Controllers Development | 4 |  | Zack | 2023-02-11 | 2023-05-11
B02.3.1 | Age Ratings Controller |  | Mauro | Zack | 2023-01-11 | 2023-02-11
B02.3.2 | Countries Controller |  | Zack | Zack | 10/31/23 | 10/31/23
B02.3.3 | Categories Controller |  | Mauro | Zack | 2023-01-11 | 2023-02-11
B02.3.4 | Ratings Controller |  | Zack | Zack | 2023-01-11 | 2023-04-11
B02.3.5 | Series Controller |  | Zack | Zack | 2023-03-11 | 2023-04-11
B02.3.6 | Authors Controller |  | Mauro | Zack | 10/31/23 | 2023-04-11
B02.3.7 | Genres Controller |  | Mauro | Zack | 10/31/23 | 2023-04-11
B02.3.8 | Languages Controller |  | Zack | Zack | 10/31/23 | 10/31/23
B02.3.9 | Covers Controller |  | Zack | Zack | 2023-02-11 | 2023-02-11
B02.3.10 | Companies Controller |  | Mauro | Zack | 2023-01-11 | 2023-02-11
B02.3.11 | Colors Controller |  | Zack | Zack | 2023-02-11 | 2023-02-11
B02.3.12 | Materials Controller |  | Mauro | Zack | 2023-01-11 | 2023-02-11
B02.3.13 | Sizes Controller |  | Mauro | Zack | 2023-01-11 | 2023-02-11
B02.3.14 | Subcategories Controller |  | Mauro | Zack | 2023-01-11 | 2023-04-11
B02.3.15 | Comics Controller |  | Zack | Zack | 2023-01-11 | 2023-04-11
B02.3.16 | Collectibles Controller |  | Mauro | Zack | 2023-01-11 | 2023-04-11
B02.3.17 | Clothes Controller |  | Zack | Zack | 2023-01-11 | 2023-05-11
B02.3.18 | Products Controller |  | Zack | Zack | 2023-04-11 | 2023-05-11
B02.3.19 | Users Controller |  | Zack | Zack | 2023-01-11 | 2023-05-11
B02.3.20 | Auth Controller |  | Zack | Zack | 2023-01-11 | 2023-05-11
B02.3.21 | Orders Controller |  | Zack | Zack | 2023-05-11 | 2023-05-11
B02.3.22 | Anouncements Controller |  | Zack | Zack | 2023-05-11 | 2023-05-11
B02.3.23 | Comments Controller |  | Zack | Zack | 2023-05-11 | 2023-05-11
B03 | API REST Testing | 2 | Zack | Zack | 2023-06-11 | 2023-12-11
F01 | React App Development | 7 |  |  | 10/31/23
F01.1 | Application Setup | 1 | Zack | Zack | 10/31/23 | 10/31/23
F01.1.1 | General Configuration | 1 | Zack | Zack | 10/31/23 | 10/31/23
F01.1.2 | Routes Definition | 1 | Zack | Zack | 10/31/23 | 10/31/24
F01.2 | CSS Styles | 1 | Zack | Zack | 2023-01-11 | 2023-01-11
F01.3 | Header Component | 1 | Zack | Zack | 2023-01-11 | 2023-01-11
F01.4 | SignIn Component | 1 | Zack |  | 2023-12-11
F01.5 | Homepage Development | 1 | Zack
F01.6 | Cart Component | 2 | Zack
F01.7 | Product Details Component | 1 | Zack
F01.8 | Product Form Component | 1 | Zack
F01.9 | Anouncements Component | 1 | Zack
F01.10 | Info Component | 1 | Zack
F01.11 | Comment Section Component | 1 | Zack